## 5 columns
C&M LEAN PROCESS
PROOFER
ACCOUNT MANAGER | ART DIRECTOR | PRODUCTION COORD | DESIGNER | Office Assistant
1. Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. Review & discuss creative direction w/ AM if AM deems necessary.
4. Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. Writes print specs, sends to Printing Services or specialty vendors for bids.
6. Print Svcs requests bids or PC contacts specialty vendors for bids. Quotes sent back to PC.
7. Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. Emails budget to client for approval.
9. Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11 Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. Reviews proofing edits. Makes changes or stets them.
13. Sends proofed copy to client for approval.
14. Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15 Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. Proofs/edits layout. Gives folder back to AM.
18. Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24/ Reviews/approves edits. Gives folder to AM.
25. Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. Proof is approved for print or edits made and new proof requested. Calls printer.
37. After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. Sends Billing Preview to AM.
41. Reviews and requests adjustment, if warranted.
42. Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column
C&M LEAN PROCESS
ACCOUNT MANAGER, ART DIRECTOR, PRODUCTION COORD, DESIGNER, PROOF READER, OFFICE ASSISTANT
1. AM - Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. AM - Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. AD Review & discuss creative direction w/ AM if AM deems necessary.
4. PC - Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. PC - Writes print specs, sends to Printing Services or specialty vendors for bids.
6. PC - Print Svcs requests bids. Quotes sent back to PC.
7. PC - Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. AM - Emails budget to client for approval.
9. PC - Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. AM - Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11. PR - Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. AM - Reviews proofing edits. Makes changes or stets them.
13. AM - Sends proofed copy to client for approval.
14. AM - Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15. DS - Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. PR - Proofs/edits layout. Gives folder back to AM.
18. AM - Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. AM - Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. DS - Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24. PR - Reviews/approves edits. Gives folder to AM.
25. AM - Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. AM - If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. PC - Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. DS - Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. DS - Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. PC - Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. PR - Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. PR - Proof is approved for print or edits made and new proof requested. Calls printer.
37. PC - After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. PC - When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) - Puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. OA - Sends Billing Preview to AM.
41. AM - Reviews and requests adjustment, if warranted.
42. OA - Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column (2)
C&M LEAN PROCESS, Website, New Development
Account Manager(AM), Web Editor(WE), Production Coordinator(PC), Office Assistant(OA), New Media Specialist (NMS) , Web developer (WD)
1 AM - meets w/client and provides ALL media options according to client needs. The AM is contact for all client requests/orders.
2 AM - initiates (opens) job in C&P. Selects Website, New development as the job type and changes the status code to 410, Website, New dev, new job opened. Enters job details in Job Ticket and Creative Brief windows. Indicates if job is a rush.
3 NMS - receives notification that a job has been opened. Creates a blank site according to creative brief or meeting.
4 NMS - sends link or the site outline to AM. Changes status code to 415 - Website, New development site concept sent to AM.
5 AM - reviews site concept with client and obtains approval. Changes status code to 418 - Website, New development, concept approved.
6 NMS - receives auto email that concept is approved.
7 AM - discusses add'l content needs, design and timeline with NMS. If no design is needed, AM changes status code to 419 - Website New development, proceed w/no design (and skip to #9).
8 AM - (If design component is needed) opens additional job in C&P. Changes status code to 420, Website, New dev. design job opened. Uses Project feature in C&P, that links this design job to the original Website New Dev. job.
(If design job is opened, PC receives auto email that design is needed and schedules/quotes per established process.)
9 NMS - receives auto email from C&P (whether a design job is opened or not) and schedules tasks per discussion with AM. Changes status code to 430 - Website, New Dev. In progress.
10 AM - Sends approved content and design to NMS to upload. Assigns writing as necessary.
11 NMS - places content and design into new site. Changes status code to 431 - Website, New dev. Ready for client review.
12 AM - receives notification and reviews website with client. Changes status code to 432 - Website, New dev. client changes received.
13 NMS receives notification and makes final changes. Changes status code to 433 - Website, New development in review.
14 WE receives notification and performs final review. Changes status code to 434, Web site, New dev. complete.
15 NMS receives auto email and enters Footprints ticket w/launch details for WD.
16 WD receives Footprints notification that website is ready for launch. Launches per instruction and notes launch in footprints ticket.
17 NMS and AM receives Footprints notification of site launch and completes friendly URL/launch sequence.
18 AM changes C&P status codes to 700.