## 5 columns
C&M LEAN PROCESS
PROOFER
ACCOUNT MANAGER | ART DIRECTOR | PRODUCTION COORD | DESIGNER | Office Assistant
1. Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. Review & discuss creative direction w/ AM if AM deems necessary.
4. Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. Writes print specs, sends to Printing Services or specialty vendors for bids.
6. Print Svcs requests bids or PC contacts specialty vendors for bids. Quotes sent back to PC.
7. Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. Emails budget to client for approval.
9. Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11 Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. Reviews proofing edits. Makes changes or stets them.
13. Sends proofed copy to client for approval.
14. Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15 Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. Proofs/edits layout. Gives folder back to AM.
18. Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24/ Reviews/approves edits. Gives folder to AM.
25. Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. Proof is approved for print or edits made and new proof requested. Calls printer.
37. After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. Sends Billing Preview to AM.
41. Reviews and requests adjustment, if warranted.
42. Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column
C&M LEAN PROCESS
ACCOUNT MANAGER, ART DIRECTOR, PRODUCTION COORD, DESIGNER, PROOF READER, OFFICE ASSISTANT
1. AM - Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. AM - Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. AD Review & discuss creative direction w/ AM if AM deems necessary.
4. PC - Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. PC - Writes print specs, sends to Printing Services or specialty vendors for bids.
6. PC - Print Svcs requests bids. Quotes sent back to PC.
7. PC - Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. AM - Emails budget to client for approval.
9. PC - Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. AM - Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11. PR - Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. AM - Reviews proofing edits. Makes changes or stets them.
13. AM - Sends proofed copy to client for approval.
14. AM - Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15. DS - Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. PR - Proofs/edits layout. Gives folder back to AM.
18. AM - Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. AM - Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. DS - Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24. PR - Reviews/approves edits. Gives folder to AM.
25. AM - Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. AM - If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. PC - Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. DS - Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. DS - Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. PC - Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. PR - Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. PR - Proof is approved for print or edits made and new proof requested. Calls printer.
37. PC - After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. PC - When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) - Puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. OA - Sends Billing Preview to AM.
41. AM - Reviews and requests adjustment, if warranted.
42. OA - Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column (2)
C&M LEAN PROCESS
ACCOUNT MANAGER (AM), ART DIRECTOR (AD), PRODUCTION COORD (PC), DESIGNER (DS), PROOF READER (PR), OFFICE ASSISTANT (OA)
1 | AM - Meets w/client and provides media options according to client needs. The AM is contact for all client requests/orders, including photo requests, printing services referrals and media buyer insertion orders.
2 | AM - Initiates (opens) job in C&P. Enters job details in Job Ticket and Creative Brief windows. Indicates if job is a rush.
3 | PC - Receives auto email from C&P indicating that a job has been opened. Writes production schedule and assigns resources (in C&P). Prints Job Ticket, Creative Brief and Schedule.
4 | PC - Writes print specs, sends to Printing Services or other vendor for competitive estimates.
5 | Printing Services estimates project or sends out for external vendor estimates. Sends estimates to PC.
6 | PC - Gives orange folder w/job production materials inside to AM. Rush jobs are put in a yellow folder = Yellow Jacket.
7 | AM - May need to meet with AD to discuss creative direction.
8 | PC - Puts print and design estimates in C&P. Changes status code to 20, Estimate ready for client.
9 | AM - Receives auto email from C&P, indicating estimate is ready. Sends estimate to client via email.
10 | AM - Prepares copy, schedules photo shoot if needed. Sends copy to proofing, changes status code on C&P to 30, Writing/copy sent to proofing.
11 | PR - Proofreads and edits copy per AP style and returns to AM. Changes status code on C&P to 40, Copy proofed sent to AM.
12 | AM - Reviews proofing edits, makes changes or stets them.
13 | AM - Emails proofed copy to client for approval. Client approves copy.
14 | AM - Emails copy, direction and photos to DS. Changes status code to 50, Writing/copy sent to design.
15 | DS - Reviews job with AD and AM, as needed. Produces 1st layout, gives orange folder w/hard copy layout (inc sign-off slug) to AD for review. Checks off Design 1st, to proofing on C&P.
16 | AD - Reviews, marks edits and makes suggestions. Puts folder in proofing box. (If major changes are required, returns folder/layout to DS.)
17 | PR - Proofs and edits layout. Gives folder to AM.
18 | AM - Reviews, marks edits, stets or approves edits/suggestions. Gives final approval and returns folder to DS.
19 | DS - Makes edits, emails PDF to AM. Files low-res PDF in Production folder (in labeled folder) on Share. Checks off PDF to AM for client, 1st task on C&P.
20 | AM - Emails PDF to client for review. Changes status code on C&P to 60, Proof sent to client.
21 | AM - Client returns 1st round proof w/edits. AM changes status code to 70, Edits received from client/send to design (indicates PC as email recipient). Adds Change Order w/details of edits (indicates DS as email recipient)
22 | DS - Makes edits (sometimes attaches a narative for client regarding design issues). Prints a hard copy. Checks off Design 2nd, to proofing on C&P.
23 | AD - Reviews, marks edits and makes suggestions. Puts folder in proofing box. (If major changes are required, returns folder/layout to designer.)
24 | PR - Proofs and edits layout. Gives folder to AM.
25 | AM - Reviews, marks edits, stets or approves edits/suggestions. Gives final approval and returns folder to DS.
26 | DS - Makes edits, emails PDF to AM. Puts low-res PDF in Production folder (in labeled folder) on Share. Checks off PDF to AM for client, 2nd task on C&P.
27 | AM - Emails PDF to client for review. Changes status code on C&P to 60, Proof sent to client.
28 | AM - Receives approval from client to print. Changes status code on C&P to 80, Client approval to print sent to design. (If edits are received from client, go to step #21.)
29 | PC - Receives auto email that job is approved to print. Completes Vendor Release, sends to OA.
30 | OA - Uses Vendor Release to complete PO req, sends to Printing Services.
31 | Printing Services signs req and sends to purchasing.
32 | DS - Fills out mail approval form and emails it, along with a PDF of the mail panel, to Printing Services for mail approval.
33 | Printing Services approves the mail panel, via email to the designer.
34 | DS - Prints final hard copy of layout. Fills out DOF and prints. Places these w/orange folder in proofing bin and checks off In preprint proofing task on C&P. Job routes to AD, PC, AM and Proofreader for final signoffs, is returned to DS.
35 | DS - Makes final edits and uploads files to awarded printer's FTP site. Creates PDF and emails with DOF to PC, puts final PDF in Production folder on Shares. Checks off Pack task on C&P. Puts orange folder in proofreader's office, for proofreader reference when printer proof is delivered to UCM.
36 | PC - Forwards PDF, DOF and Vendor Release to printer, cc Printing Services. Changes status code on C&P to 90, Job sent to printer. Emails AM - confirming quantity, delivery date/destination.
37 | PR - Receives final print proof from printer (in proofing bin). Prints Vendor Release from Share (after adding sign off slug), proofreads, signs off, staples Vendor Release to proof, routes to DS and AD for sign off.
38 | PR - Calls printer to pick up approved proof. (If proof isn't approved, printer supplies new proof, go back to #35).
39 | PC - Job delivers, PC checks off Delivered task and changes status code to 700, Ready to bill on C&P.
(If job is delivering late, printer notifies PC. PC enters new date on schedule and changes status code on C&P to 100, Job delivering late, auto email is sent to AM.)
40 | OA (OR STUDENT) - Puts printed samples in mailboxes of AD, DS, AM and PC. Files archives samples.
41 | OA - Sends billing preview to AM.
42 | AM - Reviews and approves or requests adjustment, if warranted.
43 | OA - Makes adjustments if needed (and approved by business manager). Prepares JV. Emails final bill to AM.
44 | AM - Sends final bill to client.