## 5 columns
C&M LEAN PROCESS
PROOFER
ACCOUNT MANAGER | ART DIRECTOR | PRODUCTION COORD | DESIGNER | Office Assistant
1. Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. Review & discuss creative direction w/ AM if AM deems necessary.
4. Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. Writes print specs, sends to Printing Services or specialty vendors for bids.
6. Print Svcs requests bids or PC contacts specialty vendors for bids. Quotes sent back to PC.
7. Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. Emails budget to client for approval.
9. Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11 Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. Reviews proofing edits. Makes changes or stets them.
13. Sends proofed copy to client for approval.
14. Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15 Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. Proofs/edits layout. Gives folder back to AM.
18. Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24/ Reviews/approves edits. Gives folder to AM.
25. Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. Proof is approved for print or edits made and new proof requested. Calls printer.
37. After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. Sends Billing Preview to AM.
41. Reviews and requests adjustment, if warranted.
42. Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column
C&M LEAN PROCESS
ACCOUNT MANAGER, ART DIRECTOR, PRODUCTION COORD, DESIGNER, PROOF READER, OFFICE ASSISTANT
1. AM - Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. AM - Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. AD Review & discuss creative direction w/ AM if AM deems necessary.
4. PC - Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. PC - Writes print specs, sends to Printing Services or specialty vendors for bids.
6. PC - Print Svcs requests bids. Quotes sent back to PC.
7. PC - Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. AM - Emails budget to client for approval.
9. PC - Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. AM - Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11. PR - Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. AM - Reviews proofing edits. Makes changes or stets them.
13. AM - Sends proofed copy to client for approval.
14. AM - Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15. DS - Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. PR - Proofs/edits layout. Gives folder back to AM.
18. AM - Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. AM - Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. DS - Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24. PR - Reviews/approves edits. Gives folder to AM.
25. AM - Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. AM - If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. PC - Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. DS - Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. DS - Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. PC - Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. PR - Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. PR - Proof is approved for print or edits made and new proof requested. Calls printer.
37. PC - After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. PC - When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) - Puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. OA - Sends Billing Preview to AM.
41. AM - Reviews and requests adjustment, if warranted.
42. OA - Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column (2)
LEAN, Video process
Account Manager(AM), New Media Specialist (NMS), Freelance Videographer (FV), Production Coordinator(PC), Kathleen Wiles (KW), Office Assistant(OA),
Deisgner (DS), Proof reader (PR), Art director (AD)
1 | AM - meets w/client and provides ALL media options according to client needs. The AM is contact for all client requests/orders.
2 | AM - Meets w/NMS to discuss project plan (creative direction, shot list) and implementation plan (where will it end up, what's the end goal?). Discusses which vendor is appropriate, if there are any other needs that will have a cost (design, photography). If Video Services is chosen, client is referred to them and UCM involvement ends.
3 | AM - Opens job in C&P. Enters job details in Job Ticket and Creative Brief windows. Inputs NMS initials in the traffic window. Indicates if job is a rush. Changes status code to 110 - Video, New job opened.
4 | NMS - Receives auto email from C&P indicating that a job has been opened. Writes production schedule and schedules resources in C&P. Prints Job Ticket, Creative Brief and Schedule. Makes a job folder and keeps it.
5 | NMS - Writes specs from creative brief, sends to FV for estimate and availability. Checks off task Specs sent to FV for estimate.
6 | FV sends estimate to NMS.
7 | NMS inputs onto C&P. Changes status code to 125 - Video estimate ready for client, UNLESS design component is needed for video.
(If design component is needed for video:)
8 | NSM changes status code to 115 - Video, design needed. Adds design direction to Creative Breif.
8b - PC recieves auto email. Reviews Creative Brief, adds estimate and schedules as required. Changes status code to 120 - Video, design estimate added. Creates folders/gives to designer.
8c - AM sends copy/creative direction to assigned designer. Changes status code to 50, writing/copy/direction sent to design.
8d - DS reviews job with AD and AM, as needed. Produces 1st layout, gives orange folder w/hard copy layout (inc sign-off slug) to AD for review. Checks off Design 1st, to proofing on C&P.
8e - AD reviews, marks edits and makes suggestions. Puts folder in proofing box. (If major changes are required, returns folder/layout to DS.)
8f - PR proofs and edits layout. Gives folder to AM.
8g - AM reviews, marks edits, stets or approves edits/suggestions. Gives final approval and returns folder to DS.
8h - DS makes edits, emails PDF to AM. Files low-res PDF in Production folder (in labeled folder) on Share. Checks off PDF to AM for client, 1st task on C&P.
8i - AM emails PDF to client for review. Changes status code on C&P to 60, Proof sent to client.
8j - AM receives client approval. Changes status code on C&P to 80, Client approval sent to design.
8k - PC receives auto email that job is approved to print. Checks off Client approval final, task on C&P.
8l - DS prints final hard copy of layout. Places w/orange folder in proofing bin and checks off In preprint proofing task on C&P. Job routes to AD, AM and PR for final signoffs then is returned to DS.
8m - DS makes final edits and sends final files to AM. Creates PDF and puts in Production folder on Shares. Checks off Pack task on C&P.
9 | AM - Receives auto email from C&P, indicating estimate is ready. Sends estimate and project plan to client via email. Changes status code to 130 - Video, need client approval of budget.
10 | AM - Receives estimate/project plan approval from client. Changes status code to 135 - Video,Client app’l est/project plan.
11 | NMS, with AM, finalizes copy/shot list (sends copy through proofing if needed). Checks off task Copy/shot list finalized.
12 | AM - Schedules shot list, sometimes w/the assistance of the NMS. Puts final schedule and/or link to final schedule on C&P. Changes status code to 140 - Video, shoot scheduled.
13 | NMS - Emails final shot list, production timeline to FV, Also confirms budget, date(s), time(s) and location(s) of shoot with FV. Checks off task Confirm video shoot with FV.
14 | NMS - (sometimes w/AM) accompanies FV on video shoot.
15 | NMS - Change status code to 145 - Video, filming complete. Checks off Video shoot task on C&P.
16 | NMS - Sends FV correct spelling of names and titles of subjects in the video. (If needed, NMS meets with FV to go over shots and select which ones to use, gives input on the flow of the video). Releases design work to FV if applicable. Checks off task Additional items, to FV, if needed.
17 | NMS - Receives first version of video for review. Puts link of video location in Creative Brief. Changes status code to 150 - Video, 1st version received. Checks off 1st version of video due from FV task.
18 | NMS - with AM - Reviews, writes up edits and suggestions. Sends back to FV. Changes status code to 155 - Video edits w/FV. Checks off Video edits due back to FV task.
19 | NMS - Receives revised video. Puts link of video location in Creative Brief. Changes status code to 160 - Video, 2nd version received. Checks off 2nd version of video due from FV task.
20 | AM - Receives auto email that video is ready to review. AM emails to client for approval. Changes status code to 160 - Video sent to client.
21 | AM - Receives approval from client. Changes status code on C&P to 170 - Client approval of video to upload. (If edits are received from client, go to step 16 until acceptable and changes status to 155 - Video edits w/FV).
22 | NMS receives auto email and checks off Client approval of video task on C&P.
23 | NMS uploads to YouTube. Checks off Upload video task on C&P.
24 | NMS Carries out implementation plan. Checks off task Implementation complete. Puts media on the server, burns a disc and places it in job folder, and gives to OA for billing/filing. Changes status code to 175 - Need final FV time.
25 | KW checks for status code 175 when bi-weekly pay is due. Adds FV time to job. Changes status code to 700 - Billing, ready to route.
26 | OA - sends billing preview to AM and copies NMS.
27 | AM - Reviews and approves or requests adjustments, if warranted.
28 | OA - Makes adjustments if needed (and approved by business manager).
29 | OA - Prepares JV. Emails final bill to AM.