## 5 columns
C&M LEAN PROCESS
PROOFER
ACCOUNT MANAGER | ART DIRECTOR | PRODUCTION COORD | DESIGNER | Office Assistant
1. Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. Review & discuss creative direction w/ AM if AM deems necessary.
4. Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. Writes print specs, sends to Printing Services or specialty vendors for bids.
6. Print Svcs requests bids or PC contacts specialty vendors for bids. Quotes sent back to PC.
7. Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. Emails budget to client for approval.
9. Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11 Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. Reviews proofing edits. Makes changes or stets them.
13. Sends proofed copy to client for approval.
14. Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15 Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. Proofs/edits layout. Gives folder back to AM.
18. Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24/ Reviews/approves edits. Gives folder to AM.
25. Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. Proof is approved for print or edits made and new proof requested. Calls printer.
37. After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. Sends Billing Preview to AM.
41. Reviews and requests adjustment, if warranted.
42. Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column
C&M LEAN PROCESS
ACCOUNT MANAGER, ART DIRECTOR, PRODUCTION COORD, DESIGNER, PROOF READER, OFFICE ASSISTANT
1. AM - Meets client and provides media options to satisfy client needs. The AM is contact for all client orders, photo requests, printing services referrals, media buyer insertion orders.
2. AM - Using standardized list, initiates job in C&P, enters all job details on creative brief, and indicates if job is a rush.
3. AD Review & discuss creative direction w/ AM if AM deems necessary.
4. PC - Receives auto e-mail indicating job has been opened. Writes prod schedule in C&P, prints job ticket, creative brief, schedule and assigns resources.
5. PC - Writes print specs, sends to Printing Services or specialty vendors for bids.
6. PC - Print Svcs requests bids. Quotes sent back to PC.
7. PC - Puts print and design estimates in C&P. Changes status code to 20 - budget ready for client.
8. AM - Emails budget to client for approval.
9. PC - Gives AM orange folder w/ sched and creative brief. Rush job = yellow jacket.
10. AM - Prepares copy, schedules photo shoot if needed, sends copy for proofing, changes status code to 30 writing/copy sent to proofing
11. PR - Proofreads, edits copy per AP Style & returns to AM. Changes status code to 40 - Copy proofed sent to AM.
12. AM - Reviews proofing edits. Makes changes or stets them.
13. AM - Sends proofed copy to client for approval.
14. AM - Sends copy/direction/photos to design. Changes status code to 50 - Writing/copy sent to design.
15. DS - Review job w/ AD & AM as needed. Produces 1st layout. Gives orange folder w/ hard copy layout and sign-off slug to AD for review. Checks off Design-1st to Proofing.
16. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
17. PR - Proofs/edits layout. Gives folder back to AM.
18. AM - Reviews, marks edits, stets or approves edits/ suggestions. Gives final approval & returns folder to designer.
19. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client 1st task
20. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client.
21. AM - Client returns 1st round proof w/ edits. Changes status code to 70 - Edits received from client/sent to design. Adds change order w/ details of edits.
22. DS - Makes edits, sometimes attaches a narrative for client re design choices & issues. Checks off Design-2nd task and puts orange folder w/ layout in AD's box.
23. Reviews, marks edits /suggestions. Puts folder in proofing box. If major changes required, returns to design.
24. PR - Reviews/approves edits. Gives folder to AM.
25. AM - Reviews, marks edits, stets or approves edits/ suggestions. Returns folder to designer.
26. DS - Makes edits, sends PDF to AM. Puts low-res PDF in BD Prod folder on share. Checks off PDF to AM for client - 2nd task
27. AM - Sends PDF to client for review. Changes status code to 60- Proof sent to client. (If revisions are required, go to step 21.)
28. AM - If approved, change status code to 80-Client approval to print/send to design. Auto e-mail sent to PC.
29. PC - Completes Vendor Release. Sends to OA.
30. Uses Vendor Release to complet PO Req. Sends to Printing Services.
31. Printing Services signs and sends to Purchasing.
32. DS - Places job w/ orange folder in proofing bin & checks off In pre-print proofing task. Routes job to AD/PC/AM/proofreader for final sign-offs.
33. DS - Job returned to designer. Makes final edits and puts files on printer's FTP. Sends PDF and DOF to PC. Puts final PDF in BD production folder on share. Checks off Pack task.
34. PC - Forwards PDF, DOF & release docs to printer, cc Printing Services. Changes status code to 90-Job sent to printer. E-mails AM delivery date and confirms quantity.
35. PR - Receives print proof from printer. (In bin.) Proofs and prints Vendor Release from share, staples to proof then routes to designer for sign-off.
36. PR - Proof is approved for print or edits made and new proof requested. Calls printer.
37. PC - After proof is approved(or edited), printer notifies PC if project will deliver late. PC enters new date onto schedule & changes status code to 100-Job delivering late. Auto e-mail sent to AM.
38. PC - When job delivers, PC checks off Delivered task and changes status to 700-Ready to bill.
39. OA (or student) - Puts print samples in mailboxes of AD, Designer, AM & PC. Files rest.
40. OA - Sends Billing Preview to AM.
41. AM - Reviews and requests adjustment, if warranted.
42. OA - Makes adjustments, if approved by Business Manager. Prepares JV. E-mails final bill to client.

## One column (2)
C&M LEAN PROCESS, Web banner
ACCOUNT MANAGER (AM), ART DIRECTOR (AD), DESIGN ASSISTANT (DA), PROOF READER (PR), OFFICE ASSISTANT (OA), NEW MEDIA SPECIALIST (NMS)
1 AM - Meets w/client and provides ALL media options according to client needs. The AM is contact for all client requests/orders.
AM - (If banner is for home page,) Sends email to NMS stating that a home page banner needs to be added to the Google calendar. AM checks Google calendar to determine if home page is booked for time slot desired. If it is, AM discusses priority of run schedules w/TM or LL.
2 AM - Initiates (opens) job in C&P. Selects Web Banner as the job type and changes the status code to 210, Web banner, New job opened. Enters job details in Job Ticket and Creative Brief windows. Indicates if job is a rush.
3 NMS - (If banner is for home page,) schedules it on Google calendar.
4 DA - Receives auto email from C&P indicating that Web banner job has been opened. Writes production schedule and assigns resources. Prints Job Ticket, Creative Brief and Schedule.
DA - (If another designer is producing banners), DA sends email to PC asking for another designer to be assigned. PC schedules/quotes as per any other design project (see print LEAN process).
5 DA - Reviews job with AD and AM, as needed. Produces 1st layout, gives orange folder w/hard copy layout (inc. sign-off slug) to AD for review. Checks off Design 1st, to proofing on C&P.
6 AD - Reviews, marks edits and makes suggestions. Puts folder in proofing box. (If major changes are required, returns folder/layout to DA.)
7 PR - Proofs and edits layout, as needed. Gives folder to AM.
8 AM - Reviews, marks edits, stets or approves edits/suggestions. Returns folder to DA.
9 DA - Makes edits, emails PDF to AM. Files low-res PDF in Production folder (in labeled folder) on Share. Checks off PDF to AM for client, 1st task on C&P.
10 AM - Emails PDF to client for review. Changes status code on C&P to 60, Proof sent to client.
11 AM - Client returns 1st round proof w/approval. AM changes status code to 215 (Web banner, client app to upload w/edits) and adds Change Order w/details of edits (indicates DA as recipient). Or changes status codes to 220 (Web banner, client app to upload).
(AM- If edits are made, AM changes status code to 213 (Web banner, client edits sent to design. Go back to #5).
12 DA - Receives auto email that job is approved to upload. Checks off Client approval final, task on C&P. If no edits are needed, removes Preprint proofing task on C&P and proceeds to step 14.
13 DA - If edits are needed, makes them and prints final hard copy of layout. Places in orange folder in proofing bin and checks off Preprint proofing task on C&P. Job routes to AM and proofreader for final signoffs, is returned to DA.
14 DA - Sends final (PNG) files to AM for upload (or for passing onto client for upload). Puts final PDF in Production folder on Share. Checks off Pack task on C&P. Changes status code to 700.
DA - (If banner is for home page) Sends final files to NMS for uplaoding. Puts final PDF in Prod . . . See above.
15 NMS - (If banner is for home page) Runs/stops running banner according to Google calendar.
16 OA - Prepares JV. Emails final bill to AM.
17 AM - Sends final bill to client.