## >$200
Projects in Progress - over $200,000 | JCOS Approval Required |  | Original Budget | Revised Project Budget | Actual Expenditures to Date | Forecast of Final Cost | Source of Funding | Proj Mgr
University Student Housing | Yes | 2000-10-17 | 21000000 | 21000000 | 20972188.25 | 21000000 | 2001 Bond Issue | Janet
Fund Number 70514, 70608, 70609, 70638
Status: Irrigation work to occur in April 2008 to finish work and project
Board of Trustees Approved: March 2000
Projected Completion Date: May 2008
Energy Services Project 05 | Yes | 2005-12-01 | 11868188 | 11868188 | 10940279 | 11868188 | Existing debt service and projected energy | Janet
Fund Number: 70625 | [6 empty] | savings
Status: Project complete, will be closed out as soon as final invoices processed
Board of Trustees Approved: October 2005
Projected Completion Date: January 2008
Meadow Brook Hall Repairs/Renovation Project / MBH Tent & Outbuilding | Yes | 2005-06-17 | 8400000 | 7055268 | 6951743.68 | 7055268 | $7.0M - Matilda R. Wilson Fund Charitable Trust | Janet
Fund Number 70589,70590 | [6 empty] | $24,000 - Motor Cities Nat'l Heritage Grant
Status: Construction - 99%, the completion of the | [6 empty] | $31,268 - MBH Reserve Fund
carpet work will be done by May 2008
Board of Trustees Approved: June 2004
Projected Completion Date: May 2008
Comment: MBH Tent & Outbuilding work canceled $1.4M
Comment: Increase $55,268 due to additional grants for gutter & arbors
HTHW Trench & Piping Project | Yes | 2005-12-01 | 5800000 | 5800000 | 5386060.48 | 5800000 | Existing debt service and projected energy | Janet/Steve
Fund Number: 70624 | [6 empty] | savings
Status: Project complete, will be closed out as soon as final invoices processed
Board of Trustees Approved: October 2005
Projected Completion Date: January 2008
South Foundation Hall Second Floor Classroom Improvements | No |  | 865000 | 821312 | 729284.41 | 821312 | $844,800 - #14488 Year End Funds | Steve
Fund Number 70640 | [6 empty] | $ 20,200 - #12147 University Technology Fund
Status: Project complete, will be closed out as soon as final invoices processed | [6 empty] | ($43,688) - returned to #14488 Year End Funds
Board of Trustees Approved: March 2006
Projected Completion Date: November 2007
Comments: Decrease due to reduction in scope, funding returned to funding source $43,688
P-3 Parking Lot Refurbishing & Expansion | No |  | 43500 | 800000 | 580695.48 | 800000 | $800,000 - #24349 Parking Improvement Reserve | Janet/Steve
Fund Number: 70653
Status: Project complete, will be closed out as soon as final invoices processed
Board of Trustees Approved: November 2006
Projected Completion Date: December 2007
Comments: Increase due to further clarity of project scope
Kresge Library Exterior Wall | No |  | 160000 | 585000 | 474149.97 | 585000 | $160,000 - #24810 Plant Renewal Fund
Fund Number 70593 | [6 empty] | $290,000 - #24810 Plant Renewal Fund '07
Status: Project complete, will be closed out as soon as final invoices processed | [6 empty] | $135,000 - #24810 Plant Renewal Fund '08
Board of Trustees Approved: November 2006
Project Completion Date: December 2007
Comments: Increase due to further clarity of project scope
Culvert Rpl - Meadow Brook Road | No |  | 360000 | 570000 | 38481.53 | 570000 | $360,000 - #24350 Capital Project Supplement Fund | Grover
Fund Number 70702 | [6 empty] | $210,000 - #24350 Capital Project Supplement Fund
Status: Construction Phase
Board of Trustees Approved: June 2007
Projected Completion Date: June 2008
Comment: Increase $210,000 as a result of contractors bids
Back-Up Generator - Phase II | No |  | 430000 | 500000 | 469380.75 | 500000 | $430,000 - #24810 Plant Renewal Fund '07
Fund Number 70664 | [6 empty] | $ 70,000 - #24810 Plant Renewal Fund '08
Status: Construction - 99%, working on punch list
Board of Trustees Approved: November 2006
Project Completion Date: December 2007
Comment: Total approved occurred in 2007 with funding from two separate years 2007 and 2008
Underground HTHW Piping Replacement | No |  | 426900 | 488900 | 488798.28 | 488900 | $426,900 - #24350 Capital Project Supplement Fund | Grover
Fund Number 70654 | [6 empty] | $ 62,000 - #24350 Capital Project Supplement Fund
Status: Construction completed, need to make change order adjustments and waiting on invoices
Board of Trustees Approved: October 2006
Projected Completion Date: November 2007
Comment: Increase $62,000 result of additional work required for the emergency repair
Concrete Repairs to Utility Tunnel | No |  | 360000 | 360000 | 17103.52 | 360000 | $360,000 - #24810 Plant Renewal Fund | Grover
Fund Number 70700
Status: Construction 80%
Board of Trustees Approved: June 2007
Projected Completion Date: January 2008
Dodge Data Center 220 A/C Replacement | No |  | 25000 | 295700 | 284946.1 | 295700 | $200,000 - #14685 FY05 Year-End Funds | Stuart
Fund Number 70604 | [6 empty] | $ 26,724 - #19542 UTS Electronic Sys Oper
Status: Project complete, will be closed out as soon as final invoices processed | [6 empty] | $ 68,976 - #19542 UTS Electronic Sys Oper . | Steve
Board of Trustees Approved: March 2006
Project Completion Date: November 2007
Comment: Increase $270,700 result of definition determined in design and actual bids
Replacement of Pioneer Drive | No |  | 262000 | 262000 | 17902.76 | 262000 | $146,000 - FY07 Year-End Funds
Fund Number 70697 | [6 empty] | $116,000 - #24810 Plant Renewal Supplement Fund
Status: Project complete, will be closed out as soon as final invoices processed
Board of Trustees Approved: March 2007
Projected Completion Date: December 2007
Automotive Antenna Instrumentation | No |  | 620000 | 620000 | 261213.75 | 620000 | $220,000 - #21758 School of Engineering Special
Fund Number 70645, 34573 | [6 empty] | Research Support
Status: Construction - 50% | [6 empty] | $400,000 - National Science Foundation Grant
Board of Trustees Approved: June 2006
Projected Completion Date: March 2008
TOTAL PROJECTS IN PROGRESS |  |  | 50620588 | 51026368 | 47612227.96 | 51026368
Notes:
1. Revised Project Budget equals the Original Budget plus all approved changes to the budget.
2. Projects are added to the report when a funding source has been identified and a plant fund is authorized for the project.
3. The project status will be reported as "Completed" when the "actual expenditures to date" equals the "forecast", TMA work
order system ties to Banner, and no additional expenditures or work is anticipated on the project.
4. A project whose status has been reported as complete to the Board, will be removed from the report for the next Board meeting.